## raodmap
DCOE TRANSFORMATION PROGRAM ROADMAP 2018
Timeline | 2017-9 | 2017-10 | 2017-11 | 2017-12 | 2018-1 | 2018-2 | 2018-3 | 2018-4 | 2018-5 | 2018-6 | 2018-7 | 2018-8
hybris
JAVA Fundation
Advanced Technology
BA
TESTING
Advanced Technology
today
A1.基于hybris的大并发可水平扩展的方案
A2.关键业务流程监控流程平台
A5.微信赠卡场景开发，基于java快速开发框架
路线图2018
路线图2019
Digital创新，sales deck，solution介绍
自动化测试框架,应用到项目#1#2
A4.AI Integrator for eCommerce
A3.China Commerce Solution

## milestone
5 GRADE A Projects Key Milestones
W | 2017-12-04 | 2017-12-11 | 2017-12-18 | 2017-12-25 | 2018-01-01 | 2018-01-08 | 2018-01-15 | 2018-01-22 | 2018-01-29 | 2018-02-05 | 2018-02-12 | 2018-02-19 | 2018-02-26 | 2018-03-05 | 2018-03-12 | 2018-03-19 | 2018-03-26 | 2018-04-02 | 2018-04-09 | 2018-04-16
Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
Sprint | Sprint 0 |  | Sprint 1 |  |  | Sprint 2 |  |  | Sprint 3 |  |  | Sprint 4 |  |  | Sprint 5 |  |  | Sprint 6
mgmt | * Code base mgmt * Project Delivery Guideline * Project Kickoff * Sub-project kickoff
A1 | * Catch up current status * Clarify project scope * Solution architecture * Major function map * Performance target
A2 | * Clarify project scope * Solution architecture design * Major function map * Technical platform selection * Demo storyline
A3 | * Catch up current status for self build part - Kevin, find YH guy if possible * Find 3 service provider, study: technology stack, cases, probability |  | * Self build part: setup demo envrionment * Start contacting 3rd, find way to collaborate
A4 | * Clarify project scope * Technical research, how to integrate with Alexa, 天猫精灵，小雅，Siri (For this part, no one has experence, the key factor to success is that closely brainstorming)
A5 | * Clarify project scope * Select wechat fast dev kit and study how to use it, set up a demo to enable wechat development. * find out 2 use cases, must be creative, joyful, simple, just the case of Starbucks

## plan_mgmt
Project | Item | Owner | Estimation (hrs) | Completed | Remained (hrs)
mgmt | * Code base mgmt | david | 8 | 20% | 6.4
mgmt | * Project Delivery Guideline | david | 8 | 0% | 8
mgmt | * Project Kickoff | david |  |  | 0
mgmt | A1 kickoff | Mingming |  |  | 0
mgmt | A2 kickoff | kairong |  |  | 0
mgmt | A5 kickoff | Xudong |  |  | 0
0
0
0
0
0
0
0

## plan_A1
Project | Item | Owner | Estimation (hrs) | Completed | Remained (hrs)
A1 |  |  | 8 | 20% | 6.4
A1 |  |  | 8 | 0% | 8
A1 |  |  |  |  | 0

## plan_A2
Project | Item | Owner | Estimation (hrs) | Completed | Remained (hrs)
A1 | A1 Project Kickoff | Mingming |  |  | 0
A1 |  |  |  |  | 0
A1 |  |  |  |  | 0
0
0
0
0

## plan_A3
Project | Item | Owner | Estimation (hrs) | Completed | Remained (hrs)
A2 |  |  |  |  | 0
A2 |  |  |  |  | 0
A2 |  |  |  |  | 0
0
0
0
0

## plan_A4
Project | Item | Owner | Estimation (hrs) | Completed | Remained (hrs)
A4 |  |  | 8 | 20% | 6.4
A4 |  |  | 8 | 0% | 8
A4 |  |  |  |  | 0
A4 |  |  |  |  | 0
A4 |  |  |  |  | 0
A4 |  |  |  |  | 0
A4 |  |  |  |  | 0
A4 |  |  |  |  | 0
A4 |  |  |  |  | 0
0
0
0
0

## plan_A5
Project | Item | Owner | Estimation (hrs) | Completed | Remained (hrs)
A5 |  |  | 8 | 20% | 6.4
A5 |  |  | 8 | 0% | 8
A5 |  |  |  |  | 0
A5 |  |  |  |  | 0
A5 |  |  |  |  | 0
A5 |  |  |  |  | 0
A5 |  |  |  |  | 0
A5 |  |  |  |  | 0
A5 |  |  |  |  | 0
0
0
0
0